## Decklog
# | Category | Description of Feedback / Issue | Impact / Risk | Recommended Action | ABS | Priority (H/M/L) | Target Completion Date | Status | Notes / Updates
1 | Access / Permissions | Additional eLog icons (oil, ballast, etc.) visible only via MARAD HQ account; not accessible to shipboard users | Limits operational visibility and testing | Expand user role permissions to allow shipboard access to additional modules | ABS | High |  | Open | ABS needs impacted vessels and example impacted users
2 | Connectivity | eLogs requires internet connectivity for secondary login; concern when underway or during outages | Risk of log unavailability and compliance gaps | Evaluate offline mode or cached login capability | ABS | High |  | Open | Reiterated multiple times. ABS comments: use orignal NSE login in browser window for the secondary E-logs login. Internet connectivity should not be required.
3 | User Roles | Chief Mate and Chief Engineer can only access Deck Log | Prevents role-appropriate log entries | Review and correct role-based access controls | ABS | High |  | Open | ABS needs impacted vessels and example impacted users
4 | Data Entry | Activity entries do not auto-populate date/time | Increases manual workload and error risk | Enable automatic date/time population | ABS | Medium |  | Open
5 | Data Sorting | Activities do not reorder by date/time | Difficult to review or audit logs | Enable chronological sorting | ABS | Medium |  | Open
6 | Save Function | Save function returns user to home screen and entries can be viewed through Amend or Update tab | Potential data loss concern | Investigate save behavior and visibility of saved entries | ABS | High |  | Open
7 | Submission Process | Submit only works for full-day entries and requires extensive mandatory fields and signatures | Time-consuming and inefficient | Streamline submission logic; allow partial saves/submissions | ABS | Medium |  | Open
8 | PIN Usage | PINs not provided; repeated manual entry required, can be can be update or changed throught the tools setting | Security + usability concern | Auto-assign PINs or reduce repeated PIN input | ABS | Medium |  | Open
9 | Amendments | Amendments strike out prior entries without visibility and require full re-signature | Audit and compliance risk | Enable view-only history and lighter amendment workflow | ABS | High |  | Open
10 | Documentation | No user manuals or guidance provided | Steep learning curve | Provide WaveSight eLogs user manuals or training material | ABS | Medium |  | Open
11 | Revision Support | Revision/approver workflow not clearly functional | Limits review and approval process | Validate and document revision support functionality | ABS | Medium |  | Open
12 | Licensing | CAPE S members lack licenses for other eLog modules (oil, ballast) | Limits testing and readiness | Expand licenses for additional modules | ABS | Medium |  | Open
13 | Shoreside Testing | Limited shoreside IT-to-IT testing support | Slows validation and troubleshooting | Schedule shoreside testing sessions | ABS | Medium |  | Open
14 | Resource Impact | ~1 hour with full team for testing | High resource cost | Improve system usability to reduce testing/training time | ABS | Low |  | Open
15 | Watch schedules | Reset time frame of watches | Audit and compliance risk | Each Bridge watch tab should span 4 hours which is typically a standard watch aboard a U.S. merchant ship. NOT the current 3-hour watches listed. For example the tab 0100-0400 would only be 3 hours where the first watch of the day is typically the 00-04. | ABS-Wendy | High |  | Open
16 | locking down sections of the decklog enties per watch to be secure from tampering | Revision/approver workflow not clearly functional enhance security. | Audit and compliance risk | We were also concerned if one officer's watch entry data could be edited or tampered with by another officer. Onboard the Sable I was able to log into two different NSE user accounts and test that yes one officer is able to edit another officer's data even after it has already been signed. | ABS | high |  | Open
17 | ports drop down | revision/approve workflow | compliance risk | It list international ports not USA or MARAD ASSOC PORTS | ABS-Wendy | High |  | OPEN
18 | Lat and Long position//Chart plotting | No place on template to record lat and long Hour reading |  | Suggestion even though a totally differenr document, need to discuss | ABS Wendy | High |  | OPEN

## ORB
Category | Type of Issue | Description of Feedback / Issue | Impact / Risk | Recommended Action | ABS | Priority (H/M/L) | Target Completion Date | Status
Lat and long position |  | can this be automatically populated ? | compliance and audit
the bunkering from tab |  | need to be able to insert text not just select from drop down | compliance and audit
GMT This per Dillon is an IMO requiremen.Times recording only in LT local time NO GMT |  | you can only use the same time and same measurements through the record book | audit USCG
NO Save button only submit |  | on records what is there no combination of what is in the tank plus what was added | audit USCG | Need to have combined amount into that space
Last known status LKS |  | It actually records your action and shows what actions were recently taken |  | what is it suppose to generate(purpose)
Pin changes has to input in the beginning before inputing data in the template |  | if this process is not completed in the beginning you loose the information that was entered
Manual inputs for Fuel type you must also input the sulphur content a well |  | Loose information no save button
Always check template at the bottom, to review your entries |  | it is remark section at the very bottom of the template review your action taken.
Draft Button not working as an action selection on the dashboard |  | I was informed per D. Kramer that that option is turned off.
Recommendation that maybe we could assist in lat and long positions in the ports so we can have that populated, including having it to populate in the template as well.
Tank Categories no software functionality | Bug | For Tank loader, the tank type has no functionallity; example, if you select a C entry, user has to filter through all tanks when that is for recording the weekly slop/waste tanks. Fuel tanks populate, lube storage oil tanks, etc. | Lack of functionality/easiblity
Tank Capacities not auto-populating | Bug | Reference Loader includes tank and capacities. Why when selecting from uploaded tanks does the Capacity not auto-populate. Lead to manual/free text errors when reference loader contains the data. | Lack of functionality/easiblity
Difference between approve and close | Functionality/process flow | What is the difference? Is the approval to signify the Chief Engineer signing the bottom of the log book page? Is close for the Master to sign the bottom of the page in the traditional paper ORB? | Lack of understanding process flow
Create time frame set to 24 hours | Functionality and reason? | Users are not able to create ORB entries from more than 24 hours previous; example transfer occurs MARCH 3, user will not be able to make the entry on March 5. User will need to use the missed entry functionality. 33 CFR 151.25(h) says 'without delay'. Why was the 24 hour setting set? | Clarification/update User Guide so crew knows that 24 hours is the critical time to not create missed entries.
For H entries Sulphur % needs to be a field for bunker transfers | Bug | If manual fuel type is free text, the software doesnt require users to enter a sulphur % | Errors in an offical document.